## Sheet1
Issue Type | Key | Summary | Status | Assignee | Due date | Priority | Comments | Labels | Reporter
Epic | DP-1 | Infrastructure and Environment Setup | Done | Stefan Gao | 2025-06-09 | Medium |  |  | Stefan Gao
Task | DP-5 | Set up AWS account, configure billing alerts, enable MFA | Done | Stefan Gao |  |  |  |  | Stefan Gao
Task | DP-14 | Provision EC2 instance for app hosting using CloudFormation | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-15 | Configure and test Security Groups for least-privilege network rules | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-16 | Set up Route 53 DNS (if needed) and configure domain settings | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-12 | Design and deploy initial VPC, subnets, route tables, and internet gateway | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-13 | Create S3 buckets with encryption and restricted public access | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Epic | DP-2 | CI/CD Pipeline with Security Controls | Done | Stefan Gao | 2025-06-16 | Medium |  |  | Stefan Gao
Task | DP-3 | Configure GitHub Actions pipeline for build, test, and deploy stages | Done | Stefan Gao |  |  |  |  | Stefan Gao
Task | DP-4 | Set up GitHub repository with branch protection and required reviews | Done | Stefan Gao |  |  |  |  | Stefan Gao
Task | DP-6 | Integrate code scanning tools (e.g., CodeQL, Trivy, or Snyk) into pipeline | Done | Stefan Gao |  |  |  |  | Stefan Gao
Task | DP-17 | Add secrets management via GitHub Encrypted Secrets or AWS Secrets Manager | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-18 | Implement automated deployment to staging environment with CloudFormation | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-19 | Add pipeline step for linting and vulnerability scanning | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Epic | DP-7 | Application and Identity Security | Done | Stefan Gao | 2025-06-23 | Medium |  |  | Stefan Gao
Task | DP-20 | Develop simple static website with login form (mocked auth) for demo | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-21 | Configure IAM roles and policies for EC2, S3, and CloudWatch | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-22 | Enforce IAM least-privilege principle using access advisor and logs | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-23 | Create IAM group/user for developer access and enable audit trail | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-24 | Set up CloudTrail to monitor IAM activity and API usage | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Epic | DP-8 | Logging, Monitoring, and Alerting | Done | Stefan Gao | 2025-06-30 | Medium |  |  | Stefan Gao
Task | DP-25 | Enable CloudWatch metrics and logs for EC2, S3, and IAM | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-26 | Create custom CloudWatch dashboards for traffic, login attempts, and failures | Done |  |  | Medium |  |  | Stefan Gao
Task | DP-27 | Define CloudWatch Alarms for abnormal traffic or unauthorised access patterns | Done |  |  | Medium |  |  | Stefan Gao
Task | DP-28 | Configure SNS notifications for triggered alarms | Done |  |  | Medium |  |  | Stefan Gao
Task | DP-29 | Optionally integrate with Grafana for visualisation (EC2-based or managed) | Done |  |  | Medium |  |  | Stefan Gao
Epic | DP-9 | Threat Simulation and Response | Done | Stefan Gao | 2025-07-07 | Medium |  |  | Stefan Gao
Task | DP-30 | Simulate brute-force login attempt using Kali Linux in isolated VPC | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-31 | Perform port scanning and log events using AWS VPC Flow Logs | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-32 | Validate if CloudWatch alarms trigger upon abnormal events | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-33 | Document incident response scenario and effectiveness of the system | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Epic | DP-10 | Hardening and Advanced Controls | Done | Stefan Gao | 2025-07-14 | Medium |  |  | Stefan Gao
Task | DP-34 | Set up WAF (Web Application Firewall) and test common rule sets | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-35 | Enable AWS Shield protection (basic tier) and understand protection scope | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-36 | Review IAM access logs and rotate keys | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-37 | Encrypt EBS volumes and enable S3 bucket versioning and encryption | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-38 | Explore use of KMS for secure secrets storage | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Epic | DP-11 | Finalisation and Documentation | Done | Stefan Gao | 2025-07-21 | Medium |  |  | Stefan Gao
Task | DP-39 | Generate Cloud Security Map visualising system architecture | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-40 | Compile screenshots, diagrams, and config snippets into final report | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-41 | Record demo walkthrough video showing secure pipeline and logging in action | Done | Stefan Gao |  | Medium |  |  | Stefan Gao
Task | DP-42 | Reflect on DevSecOps challenges and submit final deliverables | Done | Stefan Gao |  | Medium |  |  | Stefan Gao